## Slide 1
Project Planning for Future Cities
PRESENTED BY
THE PROJECT MANAGEMENT INSTITUTE
DELAWARE VALLEY CHAPTER &
THE FUTURE CITY COMPETITION
PHILADELPHIA REGION
Notes: Instructor's Notes:
Handbook, p. 5, PM: “… the success of a project often hinges on proper management of the project goals. PM is a professional organizing system that focuses on keeping projects and teams coordinated and moving forward. “

## Slide 2
Project Plan Deliverable - 10 Points
Set Goals
Develop a schedule
Check-in and Report
Reflect and share what you have learned
More important! Plan how you will earn the other points
For More information go to the Program Handbook p. 42:
https://futurecity.org/2019-2020-future-city-program-handbook
Planning can help you to achieve all your goals
Notes: Introduce self and organizations
Discuss Project management with a focus on project planning.
FC project planning has 2 benefits:
10 points for the project plan deliverable
Main benefit is a road map for achieving your goals
Review the 4 project plan components

## Slide 3
What You Will Learn
How to score the 10 project management points
Setting project goals
Deciding which goals are worth your effort - prioritizing
How to plan ahead
How to break big jobs into smaller objectives
How to follow a plan
How to deal with unknowns
How to adapt to changes
How to make the best use of time and money
Apply the time-tested principles of project management
to reach your goals.
Notes: The Handbook has a lot of information and can be overwhelming.
Divide up your work and set priorities

## Slide 4: Goals and Objectives - “Why?”
Why are you participating in Future Cities Competition ?
Win the competition?
Do better than last year?
Learn about careers?
Have fun?
Learn something new?
Meet other people?
Travel to the Nationals ?
Add an activity to your resume?
Collaborate with a group?
Prioritize this list for the Goal section of the Project Plan form
Notes: Ask why the participants are in the Future City competition
Each team should brainstorm together why they are in the competition.
Review the reasons here:
Discuss how one of the main goals of the competition is to provide experience with every discipline of engineering
Winning special awards might be a realistic goal: PMI award, First winners award, best moving part

## Slide 5: Initiating a Project
Think about it
Write it down
Reach agreement
Put the Final Objectives into the Project Plan
Notes: This is the process for determining objectives:
Brainstorm, prioritize, and reach agreement
This will be an important input into planning
For the Future Cities competition fill-in the objective section

## Slide 6: Plan: Determine How to Do It
A plan fits the pieces of your project together
Risk
Scope
People
Time
Purchasing
Cost
Quality
Communication
Notes: Instructor Notes:
One nice thing about planning, it can be divided up into smaller pieces.
These also occur in order.
The project manager works on making sure they all fit back together again.
Discuss the 8 main planning groups above
These areas are all iterative in nature because each may impact each other. (the same as the Engineering processes as described on p. 13)
You must plan out your project before jumping into it to save time and reach your objectives
Emphasize the quality of the model: it should not look like recycled material
Communications is important: team members working at different times should be on the same plan

## Slide 7: Plan Scope “What?”
Fill-in the assumption section of your plan.
Scope
  What are the deliverables?:
    Project Plan (10 Points)
    Virtual City Design (48 points)
    City Essay (60 points)
    City Model (70 points)
    City Presentation (70 points)
  Get input from your stakeholders
  “Collect requirements”
Define the project’s output in detail
  Select only one threat to the water supply
  Includes water storage and transport
  Need two innovations (see p. 30)
Assumptions
Notes: Instructor's Notes:
When creating the scope :
  Determine the deliverables (See Handbook, p. 41-61)
  What are the assumptions you are making  this goes into the Future Cities’ Project Plan
  At this point also think about your critical stakeholders, they should help with scope
  Also begin to think how your work can be broken down into logical groups
  P. 57 threats can include drought, flooding, population change, natural disaster, economic recession
Who are the stakeholders on this project?
Team members, mentor, teacher, regional coordinator, judges

## Slide 8: Example Requirements
  Functional Requirements
    Resilient water supply for a City
    Zones (residential, commercial, industrial)
    Health of residents, including vulnerable populations
    Last 100 years
  Constraints on how the work must be done
    The team will work after school
    Meetings must be at the school with mentors
    Drafts/prototypes must be reviewed by 12/4/2019
    Final design must be done by 12/18/2019
Fill-in the constraints section of your plan.
Scope
Put the constraints and assumptions into the Project Plan form
Notes: Instructor's Notes:
The handbook uses the term specifications a lot. Requirements is a similar term.
Here are some examples of functional requirements.
What are some of the requirements for your projects? Remember, they should answer the question “what” will your project do or deliver.
From the handbook: the city should last 100 years into the future
Virtual city: must use the slideshow template
Choose a region
Progress at 2 points in time
No sandbox mode, off-line preferable
Turn off random disasters
No cheat codes,
PDF format

## Slide 9: Work Breakdown Structure
Define the high-level work to be done.
Scope
Notes: Instructor's Notes:
Break you projects into parts.
This diagram is based on the deliverables, which is a very good approach
There are others, maybe see what the water treatment industry uses.
Another could be Define, Plan, Do, Review (Handbook outline, graphic p. 4,15) or Design, Build, Show (cover, and further defines ‘Do’ see graphic p. 13)
The handbook p. 23 says all work is not a straight line, progress is not from the SimCity Design to the essay.
The essay might have to be updated after the model and presentation are done.
Take dependencies into account when creating your schedule
Also, organize the requirements following the WBS:
The city model has to be made of recycled material, 1 moving part, built to scale, < $100
The city presentation has to be presented by 3 students, have display boards, handout/brochure is acceptable, costumes are recommended.
This makes it easier for everyone to focus on their part of the project and improves the chance of getting it right

## Slide 10: Plan Time - “When?”
Define the detailed activities for each deliverable
Put the activities in sequence
Estimate the calendar time (days or weeks) for each activity
Create a schedule
Start thinking about the skills that are needed
Determine the order and duration of activities.
Time
Fill-in the schedule part of the Project Plan form
Notes: Instructor's Notes:
  Discuss the activities which must be done in the order below:
  Define activities
  Sequence Activities  don’t forget your dependencies
  Determine Resources needed
  Estimate Time for the activities
  Develop a Schedule

## Slide 11: Example Activity List
Fill-in the schedule section of your project plan
Time
Activities for the “City Essay Research” WBS Element
Activity | Labor | Resources
Read the rubric | 1 hour | Future Cities Handbook
Brainstorm | 3 hour | Project team
Organize the ideas | 2 hours | Brainstorm notes
Create an outline | 2 hours | Ideas, author
Notes: Instructor's Notes:
Decompose the work packages created in the WBS to activities
Determine the activity resources needed
Estimated how much time each activity will take
Develop the schedule
Make sure your schedule is realistic
Don’t get too complicated
Don’t correct people if they are late, make better estimates the next time
For a sample of some project activities see the Handbook: mentors p. 9, students p. 16.

## Slide 12: Plan Cost
Estimate how much each activity will cost
Include the cost for
  Labor ← Volunteers/students so $0
  Supplies ← Provided by the school, parents $0
  Overhead (like office space and equipment)
Add the estimates to determine the total cost of your project
Estimate the cost of your project
Cost
Notes: Instructor's Notes:
Volunteers and $0 costs sounds great. Really this is a constraint and is something that has to be planned.
What are some of the problems with using volunteers?
Get the best use of the volunteers time, consider the other things they could be doing (opportunity cost)
Make it fun.
For model supplies make sure the value of the gifts are included and costs < $100.
The registration fee is not included in the $100 limit.

## Slide 13: Plan Cost: Example
Roll-up the cost of each activity, to the elements, and project .
Cost
Activity | Labor | Resources | Labor Cost | Supplies Cost
Sim City model | 80 hours | Students, software | $0 | $98
Virtual City design | 40 hours | Students, material | $0 | none
Presentation | 20 hours | Students, software | $0 | none
Essay | 15 hours | Students, software | $0 | none
Notes: Instructor's Notes:
  Describe the spreadsheet of labor and cost
  Make a budget for each deliverable and the whole project.
  Monitor the cost and schedule at the deliverable so it is easier to fix problems.
  Also look at the whole project.

## Slide 14: Plan Quality - “How?”
Determine what quality means for your project
Determine how you will ensure quality
Ensure your project produces quality outputs.
Examples
Quality means:
  No spelling/language errors
  SimCity model works
  The presentation is 7 minutes and free of defects
  Workmanship of model
How we will ensure quality:
  Independent document reviews
  SimCity model testing
  Review documents and products for consistency
Quality
Notes: Instructor's Notes:
Workmanship of the model is very important. It should look like roads and a building, not newspaper.
Get everyone to agree on the quality level.
Define a process for checking quality.
Everyone checks their own work.
Someone else must check all work: teacher, mentor, parent
Maybe quality is a sanity check: ask someone else if it just makes sense.
Consider consistency: all roads should look similar. Create a style guide. How about branding?

## Slide 15: Plan Risk - more “What?”
Risks are uncertain future events that can affect your project
There are two types of risks
  Threats have a negative impact on your project
  Opportunities have a positive impact on your project
If you know about a risk, you can manage it.
Risk
Notes: Instructor's Notes:
  The project risks that you identify are things that impact your cost, schedule scope.
  Risk can be both positive and negative
  A risk: the city model does not work, no one understands the software,
  An opportunity: the project plan and essay are done early, the resources can be used for other deliverables

## Slide 16: Plan Risk
Take initiative to reduce threats and increase opportunities!
Risk
  Talk to others
  Make a list
Identify
  Probability – How likely is it to happen?
  Impact – How big of an effect will it have?
Assess
  Include activities to change probability
  Include activities to change impact
  Include cost or time buffers
Plan
Notes: Instructor's Notes:
  Get the team together and brainstorm what can go wrong and right with a project.
  In brainstorming no idea is a bad idea. The goal is to build on other’s ideas.
  Then assess which risks are most likely to occur, and have a big impact on the project.
  Plan how are you going to prevent some risks from happening  put these activities in the schedule
  Plan how you will react to other risks if they happen
  Example: the batteries could die when demonstrating the moving part? Bring spares, or, put in spares right before judging.
  Exercise: brainstorm some of the things that can go wrong or opportunities you might find on your project

## Slide 17: Plan Risk: Example
Be proactive – stop problems before they happen!
Risk | Probability | Impact | Owner | Action Plan
SimCity does not work | Medium | High | Bob | Obtain and expert
Content for Presentation | High | Med | Joe | Review a prototype
City design is not practical | Medium | Med | Bob | Review existing technology
Mentor busy in work | Medium | Med | Jane | Identify additional mentors, talk to other teams
Judges do not like deliverables | Low | High | Joe | Discuss approach with other team leaders
Risk
Notes: Instructor's Notes:
Review these risk examples,
The plan should be easy to understand and use.
Regional directors can assist with additional mentors

## Slide 18: Plan Purchasing
Determine what goods and services you need
Determine how you will acquire them
Have what you need at the time that you need it.
Purchasing
Examples
What you need:
  Model material
  Computers
  Software
  Experts
How to acquire:
  Stores
  On-line
  School
  Volunteer
Notes: Instructor's Notes:
Purchasing is not an important part of the Future Cities’ Competition. Plans are always tailored or adjusted to the unique characteristics of the project.
On large projects some of the requirements are passed on to consultants and contractors.
Planning should still occur for this competition. Make sure all of the equipment, software, and materials is available when people are making the deliverables.

## Slide 19: Plan People - “Who?”
Acquire your project team
Assign your project team members to roles
Assign your project team members to activities
Train your project team
Determine how you will motivate and reward your team
Fill-in the Resources section of the Project Plan.
People
Notes: Instructor's Notes:
Managing people is usually more complex than acquiring material and equipment.
People want to do it “their” way.
There can be conflict over who will do parts of the project.
Sometimes it is difficult to motivate volunteers.
What are some of the solutions:
First of all plan  which is what we are doing now.
Use those style guides and requirements to guide people’s work.
Recognize volunteers and other hard workers.
Agree on how conflicts will be resolved.

## Slide 20: Plan People: Example
Organize your team for roles and activities.
Responsibility Assignment Matrix
Activity | Team Members |  |  | 
 | Joe | Bob | Jane | Betty
Essay | P | S |  | 
Plan |  |  | P | 
Design |  |  |  | P
Model | S | P | S | S
Presentation | P |  |  | 
P=Primary Responsibility
S=Secondary Responsibility
Joe
Bob
Jane
Betty
Organization Chart
People
Notes: Instructor's Notes:
Example : Use a RAM (Responsibility Assignment Matrix) to assign team members and responsibilities
Organization charts can be used to identify leaders
Consensus might be a good way to make decisions, at least fair.
Part of life is learning to work through conflicts, this is an important tool for your career.

## Slide 21: Plan Communication
Communication is essential for project success
Poor communication can cause:
  Misunderstandings
  Wasted time and effort
  Low project team morale
90% of a project manager’s time is spent communicating.
Communication
Types of Communication
Internal and External
Vertical and Horizontal
Written and Oral
Verbal and Non-verbal
Formal and Informal
Official and Unofficial
Notes: How do you communicate to other team members who are working at different times?
Maybe some team member are working at home (?)
Think about remote access, cloud computing, collaboration tools
Maybe one point of contact for external communications

## Slide 22: Communication Skills
Purpose | Skill
Hear what others are really saying | Active listening
Understand and uncover deeper meaning | Questioning and probing
Tell others what they can expect | Setting and managing expectations
Increase knowledge | Educating
Improve performance | Coaching
Convince others to act | Persuading
Encourage the team | Motivating
Minimize disruption due to conflicts | Resolving conflict
Use the skill to achieve the results you want
Communication
Notes: These are some skills that can be used to improve communications
Project Management is about leadership, motivating and influencing skills are very important

## Slide 23: Plan Communication: Example
Stakeholder | Frequency | Type | Purpose
Judge | Once | Written | The essay provides a description of how the water supply is resilient
Team | Daily | Oral | Overall plan for the project and daily updates as project progresses
Team | Once | Demonstration | Instruct team on the design for water storage and distribution
Mentor | Daily | Oral | Provide updates on the progress of the project at the end of each day and if there are any issues with completion
Plan to communicate – who, when, how, and why.
Communication
Notes: Beginning every work session with a 5 minute stand-up meeting is a great way to communicate what everyone is working on and problems they are having. Figure out the solution later, and don’t report status.

## Slide 24: More About Plans
  Write down your plan
  Compare your plan to your Project Objectives and address differences
  Get agreement from stakeholders
    Sponsor
    Mentors
    Project Manager
    Project Team
  Measure your project progress against your plan
  Know that your plan will change
Your plan is an agreement of how to accomplish your goal.
Notes: Instructor's Notes:

## Slide 25: Plan: Determine How to Do It
An integrated plan shows you how to reach your goal.
Risk
Scope
People
Time
Purchasing
Cost
Quality
Communication
Notes: Instructor Notes:
Now, put the pieces of your plan back together again. Everyone should think the plan can be accomplished.
Everyone should know how their part fits in. Remember the organization part of project management? The PM is the only person who can integrate and bring the entire plan together.
If you’re thinking you don’t have enough time, streamline your plan. Make sure it’s not too complicated.
Next year maybe start on the plan earlier.
Build upon your plan from this year.
Project plan scoring: submit complete, on time 10 pts; incomplete or late 5 pts; not submitted 0 pts (p. 42)

## Slide 26: Execute
Now that you have a plan, follow it.
Monitor and Control
Initiate
Execute
Plan
Close
Determine how to do it
Do it
Decide to do it
Wrap it up
Adapt to change
Notes: PMBOK definitions:
This is similar to a diagram in page 15 of the handbook
Initiate is the same as define objectives
Execute is the same as do.
Close is the same as review.
Monitor and control is where your project reports get created.
We now have an approved plan and are doing the work.

## Slide 27: Execute – Project Manager’s Role
The Project Manager has overall responsibility for the project.
  Carry out your plan
  Organize and train the project team
  Assign work to the project team
  Direct and manage the team’s activities
  Communicate with stakeholders
  Measure your progress against your plan
  Measure quality against your plan
Project Manager
Notes: This is normally the project manager’s job during execution.
Do you think your teams should have a project manager?

## Slide 28: Execute – Other Roles
People are the key to success!
  Does the work
Project Team
  Funds the project
  Promotes the project
Sponsor
  Stay informed and engaged
Stakeholders
Notes: Instructor’s Notes
Explain what is the executing process and what the project manager does during execution

## Slide 29: Execute
Follow your Plan
  Scope
  Time
  Cost
  Quality
Produce the Output
  Product
  Service
  Result
A good plan makes executing easier.
Notes: The purpose of the execution phase is to develop and produce the project’s expected deliverables on time, on budget, and meet the agreed-upon scope and fulfill customers quality requirements.
Scope defines the product.
The product is your model, essay, plan, presentation
The people doing creating the city presentation hopefully reviewed all of the requirements and specifications and are now creating the city.

## Slide 30: Monitor and Control
Update the Check-in section of the project plan.
Monitor and Control
Initiate
Execute
Plan
Close
Determine how to do it
Do it
Decide to do it
Wrap it up
Adapt to change
Notes: Monitor and control is where the work being executed is being compared to the plan.
Do the deliverables meet the requirements and specifications?
Are the activities being completed on time?
Are the actual costs for the deliverables the same as the budget?
Is quality better or worse than the plan? Is better quality a problem?
How are the resources performing?
Create reports that show the differences, or, that hopefully everything is on track.
The plan might have to be changed if there are any large differences. Maybe communications or resources are not working out.

## Slide 31: Recognize Change
Recognize that change is happening
Uncover the cause of the change
Decide what to do
Adjust your plan
Execute your adjusted plan
Notes: Instructor’s Notes
This is the process for managing change if there are large differences from the plan.
Usually only the symptom of the problem is apparent.
Sometimes you have to look very hard to find a symptom. Try to capture problems before they become big.
Look for root cause (5Y’s).
One common source is a change in scope, changing what is going to be done.
In all cases:
Figure out a solution. Get approval.
Change your plan.
And make sure the change gets implemented.

## Slide 32: Making a Decision
Control the change – don’t let it control you.
Recommend action
  Corrective action
  Preventative action
  Defect repair
Get agreement
  Talk to the people who are affected
Accept or reject the change
  Write down the decision
Notes: Instructor’s Notes
Create a process for making decisions on your project.
What’s the best method: democracy, consensus, dictator?
What are some of the decisions that have to be made: making a city that will last 100 years, where to plan roads, industrial zones, making team changes

## Slide 33: Adjust Your Plan
Determine how your decision affects each aspect of your plan.
Adjust your plan to reflect the change.
Involve stakeholders in the process.
Keep your plan up-to-date with your decisions.
Risk
Scope
People
Time
Purchasing
Cost
Quality
Communication
Notes: Instructor’s Notes
Typically there is a review and approval process before the plan is changed.
At any rate, make sure that approved changes are communicated to everyone

## Slide 34: Close
Cross the finish line!
Monitor and Control
Initiate
Execute
Plan
Close
Determine how to do it
Do it
Decide to do it
Wrap it up
Adapt to change
Notes: What kind of work is left after everything has been completed and the work is all done?
Clean-up
Put everything away
How about get ready for next year?

## Slide 35: Close: Wrap It Up
  Make sure that the plan’s scope is complete
  Make sure that the plan’s activities are complete
  Make sure that the plan’s outputs are produced and accepted
Confirm that the project is finished
  Save records that can help a future project
  Gather lessons learned and save them for the future
Collect records
  Turn over the project’s output to whoever will use it
  Make sure deliverables and supplies are inventoried
  Get agreement that everything is finished
  Celebrate and thank everyone!
Satisfy stakeholders
Notes: Ask the teacher and mentor to conduct acceptance testing of the deliverables.
The judges of course will be the final users of the deliverables.
Clean-up the meeting area, put all of the supplies away, follow-up with the teacher on any grades
Include in your plan a celebration for all the team members and acknowledge the volunteers

## Slide 36: Close: Lessons Learned
Talk to everyone involved and get honest feedback
  What went well
  What you could improve next time
  What you achieved
Write it down so you remember it for the next project
Update the Reflect section of the Project Plan
Notes: What are some of the things you are going to try this year. Write them down in Lessons Learned log now.
Update the log as the project progresses.
Finalize them after the regionals or nationals.
Ask the mentor to review the lessons learned log.
Reflect before and after the competition

## Slide 37: The Importance of Planning
From the Handbook, p. 24:
“We created an awesome city because we took the time to think about our goals and came up with a clear plan.”
-Student Participant
Notes: Questions:
Do you think planning can help with your project?
This was a lot of information, does it provide a good overview of project management?
Is anyone thinking about a career in project management?

## Slide 38: Who We Are
Project Management Institute
  The PMI is an international organization founded to:
        Promote professional project management principles and techniques;
        Create and deliver an educational program that strengthens local project management professionals' skills;
        Provide world-class PMI certification and training
Delaware Valley Chapter
  The local PMI chapter serving the Greater Philadelphia area, South Jersey, Delaware, Eastern Shore Maryland.
Notes: Instructor's Notes:
There are more than 700,000 certified project management professionals around the world.
The Federal Government is defining career paths for all agencies
The demand for project managers is increasing.

## Slide 39: Acknowledgement
The “Managing Life’s Projects” program was created by the Project Management Institute - Delaware Valley Chapter.
PMI Educational Foundation supports the chapter’s efforts to bring project management to nonprofit, civic, and community organizations. The program is available at www.pmief.org.
Notes: Versions of this presentation are being used with organizations such as School Districts and Habitat For Humanity.
Check out the PMI and PMIEF web sites.
The full Managing Life’s Projects presentation is available for download at the link shown here.
Hopefully this presentation for Future Cities will be made available.

## Slide 40: Contributors
Executive Sponsor: James Snyder
Co-Authors:
Marie Hegarty
Jerry Pearson
Major Contributors:
Ramesh Arumugam
Kristi Baldwin
Marcos Beolchi de Arruda
John A. Gaffney
Carol L. Haines
Matthew D. Rusnak
Vicki Sama
Haifa Tyler
Robert Weidner
Sandra Williams
Special Thanks to John J. Byrne, Ph.D., PMP:
Dr. Byrne was a prime contributor to the K-12 curriculum developed in 2009 by
PMI-DVC which was presented first at the Philadelphia School District Offices,
and later, at three area high schools. He was the lead instructor for the pilot
program in the School District. He generously permitted the current team to
benefit from his leadership, knowledge, and experience teaching Project
Management.